## 2024 Actions
Action Description | Proposed Activities | Priority Level | Related Natural Hazard(s) | How would this benefit underserved communities and socially vulnerable populations? | Lead Office, Division, or Department | Funding Sources | Timeline
Advance equitable community resilience, with a focus on disadvantaged communities. | Work with community partners to co-create solutions to improve community resilience, including through the Climate Equity Collaborative. | High | Multihazard | The Climate Equity Collaborative represents underserved communities, and will directly benefit these communities through meaningful involvement to identify needs and priorities. | Planning Department: Office of Energy and Sustainable Development | Seed funding secured through the Climate Equity Fund Pilot ($100,000 for the Climate Equity Collaborative) | Ongoing
Advance equitable community resilience, with a focus on disadvantaged communities. | Develop General Plan Environmental Justice Element and update the existing Safety Element, with community-identified priorities related to climate adaptation. | High | Multihazard | Direct benefit through involvement to identify needs/solutions | Planning Department: Land Use Division Planning Department: Office of Energy and Sustainable Development | Funding obtained through a $497,042 Adaptation Planning Grant Program from the CA Governor's Office of Planning and Research. City General Fund and Enterprise Fund. | Short term (1-5 years)
Collaborate with partners to increase the security of Berkeley’s water supply from climate change impacts. | Support EBMUD through the design and environmental review process to expand recycled water pipelines in Berkeley and inrease the security of the water supply. | Low | Multihazard | Water security and efficiency will have financial benefits in addition to environmental benefits, especially for disadvantaged and/or low-income communities. | Public Works Department Planning Department: Office of Energy and Sustainable Development | Federal funding from Water Resources Development Act and EBMUD | Long term (5-10 years)
Collaborate with partners to increase the security of Berkeley’s water supply from climate change impacts. | Continue to partner with agencies such as EBMUD and StopWaste to encourage private property owners and public agencies (including the City government) to use sustainable landscaping techniques that require less water and energy to maintain. | Low | Multihazard | Underserved communities are most impacted by climate change. | Planning Department: Office of Energy and Sustainable Development | City General Fund City Permit Service Center Fund City Enterprise Fund | Ongoing
Collaborate with partners to increase the security of Berkeley’s water supply from climate change impacts. | Encourage water efficiency and conservation in existing buildings. | Low | Multihazard | Water efficiency and conservation will have financial benefits in addition to environmental benefits, especially for disadvantaged and/or low-income communities. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Collect and share information with the Berkeley community about hazards and associated risk reduction techniques. | Create new formats and user friendly guidance to educate the public, especially underserved populations, on Berkeley hazards. | High | Multihazard | Ensure that underserved communities have access to hazard information and materials. | Fire Department - Office of Emergency Services | City General Fund | Ongoing
Collect and share information with the Berkeley community about hazards and associated risk reduction techniques. | Provide key hazard information and best practices to Berkeley's business and arts community through established networks, for example by exploring opportunities for local business to share best practices and resources during utility interruptions. | High | Multihazard | Small businesses, arts organizations, and nonprofits often serve socially vulnerable populations. Small businesses and cultural institutions themselves run on small margins and are especially vulnerable to shocks and stresses. | City Manager's Office - Office of Economic Development | City General Fund | Ongoing
Complete the ongoing program to retrofit all remaining non-complying Unreinforced Masonry (URM) buildings. | Continue to work with owners of remaining potentially hazardous URM buildings. | High | Earthquake | Multi-unit housing is more affordable and serves a large percentage of socially vulnerable and underserved communities. Inspections help to ensure the safety of this housing stock. | Planning Department: Building and Safety Division | Hazard Mitigation Grant Program (HMGP) | Ongoing
Continue appropriate seismic and fire safety analysis based on current and future use for all City-owned facilities and structures. | Continue analysis of structures supporting critical emergency response and recovery functions, and make recommendations for structural and nonstructural improvements. | High | Multihazard | City facilities and structures serve socially vulnerable populations day to day and during emergencies. | Public Works Department: Supervising Civil Engineer for Facilities | City General Fund T1 Bond | Ongoing
Continue implementation of the Soft Story Retrofit Program, which mandates seismic retrofit of soft story buildings with 5+ residential units. | Continue to inform impacted property owners of the requirement to seismically retrofit their buildings, including newly added properties to the soft story inventory. | High | Earthquake | Multi-unit housing is more affordable and serves a large percentage of socially vulnerable and underserved communities. Inspections help to ensure the safety of this housing stock. | Planning Department: Building and Safety Division | Hazard Mitigation Grant Program (HMGP) | Ongoing
Continue to implement the Retrofit Grants Program, which helps Berkeley building owners increase safety and mitigate the risk of damage caused by earthquakes. | Assist participating property owners with the grant process, including dissemination of program rules and guidelines and approving design and disbursement construction grants. | High | Earthquake | Multi-unit housing is more affordable and serves a large percentage of socially vulnerable and underserved communities. Inspections help to ensure the safety of this housing stock. | Planning Department: Building and Safety Division | Hazard Mitigation Grant Program (HMGP) | Ongoing
Continue to monitor passage and implementation of mandatory seismic retrofit ordinances for concrete buildings in other jurisdictions to assess best practices. | Continue to monitor mandatory seismic retrofit ordinances for concrete buildings passed by other municipalities for effectiveness and best practices. Communicate and collaborate with other cities and Structural Engineers Association of California (SEAOC) regarding implementation challenges and successes. | High | Earthquake | Multi-unit housing is more affordable and serves a large percentage of socially vulnerable and underserved communities. Inspections help to ensure the safety of this housing stock. | Planning: Building and Safety Program and Administration Manager | City General Fund | Ongoing
Coordinate regional wildfire mitigation strategies with key partners and stakeholders | Coordinate local fire mitigation, prevention, and funding strategies with the East Bay Hills Wildfire Prevention Coordination Group | High | WUI Fire | Wilfires disproportionately impacts people with access and functional needs and collaborating with local partners helps reduce wildfire risks. | Fire Department - WUI Division | City General Fund Measure FF | Ongoing
Coordinate regional wildfire mitigation strategies with key partners and stakeholders | Coordinate regional efforts to mitigate wildfire risk in the Oakland - Berkeley hills through the Hills Emergency Forum | High | WUI Fire | Wilfires disproportionately impacts people with access and functional needs and collaborating with local partners helps reduce wildfire risks. | Fire Department - WUI Division | City General Fund Measure FF | Ongoing
Coordinate with and encourage mitigation actions of key City partners. | Coordinate with and encourage mitigation actions of institutions serving the Berkeley community. | High | Multihazard | Benefits institutions serving the Berkeley community. | Fire Department: Office of Emergency Services | City General Fund Measure GG | Ongoing
Implement energy assurance strategies at critical facilities. | Identify potential actions to mitigate energy assurance vulnerabilities at critical City facilities during planning/conceptual design of both retrofits and new construction. | Medium | Multihazard Utility Interruption | City facilities and structures serve socially vulnerable populations day to day and during emergencies. | Public Works Department: Supervising Civil Engineer (Facilities) | CIty General Fund T1 Bond Measure GG Ratepayer funds from PG&E East Bay Community Energy Grants from Energy Foundation Urban Sustainability Directors Network California Energy Commission California Air Resources Board | Ongoing
Implement energy assurance strategies at critical facilities. | Provide guidance to help the City consider opportunities to design, finance and implement clean energy assurance strategies (e.g., photovoltaic-supplemented generation, energy efficiency activities, and/or mobile charging stations). | Medium | Multihazard Utility Interruption | Clean energy assurance solutions could provide backup and dritical power benefit underserved communities who wouldn't otherwise have access to power during an emergency. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Implement energy assurance strategies at critical facilities. | Work with partners to identify additional non-City critical facilities and develop strategies to provide clean backup power at these sites. | Medium | Multihazard Utility Interruption | By working with organizations serving disadvantaged communities to help advance their energy assurance, this would directly benefit both underserved organizations and community members served by these organizations. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Implement existing City programs, plans, and projects designed to reduce emissions that contribute to poor air quality. | Continue to implement the traffic safety capital construction projects identified and prioritized in the Berkeley Pedestrian Plan (2021), Berkeley Bicycle Plan (2017), Berkeley Vision Zero Action Plan (2020), and Berkeley Transit-First Implementation Plan; these projects are intended to encourage non-driving modes | Medium | Extreme Heat Poor Air Quality | Poor air quality disproportionately impacts communities of color, and South and West Berkeley. | Public Works Department - Transportation Division | City General Fund County Transportation Sales Tax | Ongoing
Implement existing City programs, plans, and projects designed to reduce emissions that contribute to poor air quality. | Continue to implement the City’s Electric Mobility Road Map which includes electric shared mobility (bikes and scooters) as well as electric and hybrid car-sharing, and the installation of public charging stations. | Medium | Extreme Heat Poor Air Quality | Poor air quality disproportionately impacts communities of color, and South and West Berkeley. | Public Works Department - Transportation Division | City General Fund County Transportation Sales Tax | Ongoing
Implement existing City programs, plans, and projects designed to reduce emissions that contribute to poor air quality. | Transportation program coordination with transit providers, Berkeley Unified School District (Safe Routes to Schools), Berkeley Police Department (Vision Zero), and others, to promote transit efficiency and traffic safety for non-driving modes. | Medium | Extreme Heat Poor Air Quality | Poor air quality disproportionately impacts communities of color, and South and West Berkeley. | Public Works Department - Transportation Division | City General Fund County Transportation Sales Tax | Ongoing
Improve responder access and community evacuation in Fire Zones 2 and 3 through roadway maintenance and appropriate parking restrictions. | Continue to enforce Fire Code requirement for fire fuel clearance on public roadways. | High | WUI Fire | Wilfires disproportionately impact people with access and functional needs and enforcing the Fire Code reduces risks. | Fire Department: WUI Division | Measure FF | Ongoing
Improve responder access and community evacuation in Fire Zones 2 and 3 through roadway maintenance and appropriate parking restrictions. | With multiple agency partners, clear hazardous vegetation along 45 roadways in Fire Zone 2 protecting evacuation routes. | High | WUI Fire | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Fire Department: WUI Division | Measure FF Cal Fire Grant | Ongoing
Improve responder access and community evacuation in Fire Zones 2 and 3 through roadway maintenance and appropriate parking restrictions. | Develop process to increase parking enforcement in fire-vulnerable areas during fire weather. | High | WUI Fire | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Fire Department: Office of the Fire Chief Public Works Department: Transportation Division Police Department: Traffic Division | Measure FF | Ongoing
Improve responder access and community evacuation in Fire Zones 2 and 3 through roadway maintenance and appropriate parking restrictions. | Maintain and improve roadways in Fire Zones 2 and 3. | High | WUI Fire | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Public Works Department: Supervising Civil Engineer | City General Fund | Ongoing
Maintain City participation in the National Flood Insurance Program. | Continue to use the most current FEMA information defining flood areas. | High | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Public Works Department: Manager of Engineering | City General Fund Permit Service Center Enterprise Fund Measure M Bond Funds Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) | Ongoing
Maintain City participation in the National Flood Insurance Program. | Continue to incorporate FEMA guidelines and suggested activities into City plans and procedures for managing flood hazards. | High | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Planning Department: Land Use Division | City General Fund Permit Service Center Enterprise Fund Measure M Bond Funds Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) | Ongoing
Maintain City programs and projects to mitigate the impacts of infectious diseases in Berkeley. | Continue surveillance and epidemiology, which is the ongoing collection, analysis, interpretation, and sharing of data in order to prevent and control disease. | High | Infectious Disease | In Alameda County, communities of color face inequitable conditions that increase the risk of chronic diseases | Health, Housing & Community Services Department, Public Health Officer Unit, Public Health Division | Public Health Emergency Preparedness Grants Future of Public Health Grant City General Fund | Ongoing
Maintain City programs and projects to mitigate the impacts of infectious diseases in Berkeley. | Implement non-pharmaceutical interventions, like personal protective measures such as masks and communitywide measures such quarantining, aimed at reducing exposure. | High | Infectious Disease | In Alameda County, communities of color face inequitable conditions that increase the risk of chronic diseases | Health, Housing & Community Services Department, Public Health Officer Unit, Public Health Division | Public Health Emergency Preparedness Grants | Ongoing
Manage and promote pedestrian evacuation routes in Fire Zones 2 and 3. | Publicize up-to-date maps of all emergency access and evacuation routes. | High | WUI Fire | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Department of Information Technology: GIS Division- GIS Coordinator Fire: OES- Emergency Services Coordinator | City General Fund | Ongoing
Manage and promote pedestrian evacuation routes in Fire Zones 2 and 3. | Maintain signage for public pathways to identify safe and accessible pedestrian evacuation routes from the hill areas. | High | WUI Fire | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Public Works Department: City Traffic Engineer | City General Fund | Ongoing
Manage and promote pedestrian evacuation routes in Fire Zones 2 and 3. | Public Works Staff will maintain paths on an as-needed basis, and will coordinate with the Berkeley Path Wanderers to maintain public pathways to provide safe pedestrian evacuation routes from the hill areas. | High | WUI Fire | Ensure that people with access and functional needs can use the pedestrian paths. | Public Works Department: Assistant Public Works Engineer | City General Fund | Ongoing
Manage and promote pedestrian evacuation routes in Fire Zones 2 and 3. | Install handrails on all public pathways, prioritizing areas with high usage and steep inclines to increase pedestrian safety and accessibility. | High | WUI Fire | Ensure that people with access and functional needs can use the pedestrian paths. | Public Works Department - Traffic Engineering | City General Fund | Short term (1-5 years)
Mitigate Berkeley’s tsunami hazard at the Berkeley Marina. | Continue to repair and replace damaged finger docks at the Berkeley Marina. Complete the demolition and replacement of D&E docks. Consider reconstruction or repair to J docks as funding becomes available. | Low | Tsunami | 10% of Marina boaters have a permit to live aboard their vessels. Many of these boaters are low-income. | Parks, Recreation, and Waterfront Department: Waterfront Division | T1 State Coastal Conservancy City General Fund Marina Fund Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) City General Fund City-Issued Bonds | Ongoing
Mitigate Berkeley’s tsunami hazard at the Berkeley Marina. | Collaborate with the California Office of Emergency Services, the California Geological Survey, and the Federal Emergency Management Agency to document and explore additional tsunami hazard mitigation measures for Berkeley’s maritime communities. | Low | Tsunami | 10% of Marina boaters have a permit to live aboard their vessels. Many of these boaters are low-income. | Fire Department: Office of Emergency Services Parks, Recreation, and Waterfront Department: Waterfront Division | Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) City General Fund City-Issued Bonds | Ongoing
Mitigate climate change impacts by integrating climate change research and adaptation planning into City operations and services. | Develop and implement a process to integrate adaptation planning into City operations, including ways to address climate impacts in municipal capital and land use planning. | Low | Multihazard | Underserved communities are most impacted by climate change. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Mitigate hazardous materials release in Berkeley through inspection and enforcement programs. | Implement the following programs: ~Hazardous Materials Release Response Plans and Inventories (HMRRP) Program ~Implement California Accidental Release Prevention (CalARP) Program ~Underground Storage Tank (UST) Program Aboveground Petroleum Storage Act Requirement for Spill Prevention ~Hazardous Waste Generator and Onsite Hazardous Waste Treatment Programs ~Implement Hazardous Materials Management Plans (HMMP) and Hazardous Materials Inventory Statements per California Fire Code | High | Multihazard Hazardous Materials Release | Hazardous materials are located in south and west Berkeley. | Planning Department: Toxics Division | City General Fund | Ongoing
Mitigate hazardous materials release in Berkeley through inspection and enforcement programs. | Enforce California Fire Code for Hazardous Materials Compliance (See Fire Code Action) | High | Multihazard Hazardous Materials Release | Hazardous materials are located in south and west Berkeley. | Fire Department: Fire Prevention Division | City General Fund | Ongoing
Mitigate hazards associated with natural gas usage, including disaster damage and energy service disruption, by minimizing need for energy use and moving toward use of electricity in lieu of natural gas. | Promote energy efficiency and electrification of buildings, both existing buildings and new construction. | High | Multihazard | City funds are targeted at underserved populations. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Mitigate impacts of sea level rise | Continue to ensure new and existing public and private developments and infrastructure are protected from floods due to sea-level rise through the permitting process for new development and conditions. | Medium | Sea Level Rise | Waterfront provides many free and low-cost recreational amenities for the community and is adjacent to lower-income communities in South and West Berkeley, which historically had fewer parks and less green space. | Planning Department: Land Use Division | City General Fund | Ongoing
Mitigate impacts of sea level rise | Identify funding and nature based solutions to adapt to sea level rise at Berkeley Waterfront areas at risk of future inundation at the shoreline at the north segment of Marina Blvd between the Virginia Street Extension and the entrance to Cesar Chavez Park. | Medium | Sea Level Rise | Waterfront provides many free and low-cost recreational amenities for the community and is adjacent to lower-income communities in South and West Berkeley, which historically had fewer parks and less green space. | Parks, Recreation, and Waterfront Department | State Coastal Conservancy Grant | Short term (1-5 years)
Mitigate impacts of sea level rise | Identify funding and nature based solutions to adapt to sea level rise at Berkeley Waterfront areas at risk of future inundation at the shoreline to the south of University Avenue between West Frontage Road and Marina Blvd. | Medium | Sea Level Rise | Waterfront provides many free and low-cost recreational amenities for the community and is adjacent to lower-income communities in South and West Berkeley, which tend to have fewer parks and green space. | Parks, Recreation, and Waterfront Department | FHWA PROTECT Discretionary Grant Program | Short term (1-5 years) (if FHWA grant received)
Mitigate impacts of sea level rise | Identify funding and nature based solutions to adapt to sea level rise at Berkeley Waterfront areas at risk of future inundation at the northeast corner of the inner harbor of the Marina. | Medium | Sea Level Rise | Waterfront provides many free and low-cost recreational amenities for the community and is adjacent to lower-income communities in South and West Berkeley, which tend to have fewer parks and green space. | Parks, Recreation, and Waterfront Department | Adapting to Rising Tides, San Francisco Bay Conservation & Development Commission, National Oceanic & Atmospheric Administration, Urban Sustainability Director’s Network, or Resource Legacy Fund | Long term (5-10 years)
Mitigate impacts of sea level rise | Conduct a groundwater study on impacts of groundwater rise combined with sea level rise on underground toxic materials | Medium | Sea Level Rise | There is a risk of underground toxic materials shifting as groundwater and sea level rise, impacting those nearby. This study will shed light on potential impacts, on places such as West Berkeley which has s a history of industrial use and environmental pollution, and is also where many low-income and disadvantaged communities live. | Planning Department: Office of Energy and Sustainable Development | This work is included in the funding obtained through a $497,042 Adaptation Planning Grant Program from the CA Governor's Office of Planning and Research | Short term (1-5 years)
Mitigate wildfire risk to Berkeley's overnight camps. | Analyze fire risk at overnight camps and identify appropriate mitigation actions. | Medium | WUI Fire | The Berkeley overnight camps offer opportunties for recreations for people with access and functional needs and people with low incomes. | Fire Department - WUI Division Parks, Recreation, and Waterfront Department | Measure FF | Short term (1-5 years)
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Continue to seek out funding to use cool paving materials on streets when feasible to reduce urban heat island impacts. | Medium | Extreme heat | Urban heat island effects are more prominent in the Berkeley flats, which are more paved and less vegetated, and which is where more underserved communities live. | Planning Department: Office of Energy and Sustainable Development | State grants from Office of Planning and Research | Ongoing
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Continue to implement energy efficiency ordinances for existing residential and commercial buildings to improve building comfort, including in extreme weather conditions, and to reduce energy use. | Medium | Extreme heat | Extreme heat in places with bad ventilation or uncomfortable conditions impact the health and wellbeing of elderly and disabled populations. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Encourage passive and energy-efficient strategies to cool buildings such as natural ventilation, shading, insulation, cool roofs, whole-house fans, and heat pump HVAC systems. | Medium | Extreme heat | Extreme heat in places with bad ventilation or uncomfortable conditions impact the health and wellbeing of elderly and disabled populations. | Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Monitor and support regional and State-level efforts to forecast the impact of climate change on temperatures and incidence of extreme heat events in Berkeley and the region, and integrate extreme heat event readiness, focusing on the most vulnerable populations impacted and improving access to resources, into City operations and services. | Medium | Extreme Heat | Low income populations have less access to resources and readiness. Extreme heat impacts the flats due to urban heat island effect, and there is a large low-income population living in the flats. | Fiire Department: Office of Emergency Services Planning Department: Office of Energy and Sustainable Development | City General Fund | Ongoing
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Continue Urban Forestry Unit's tree maintenance and planting programs to increase canopy coverage for extreme heat events to provide shade and mitigate impacts from poor air quality. | Medium | Extreme Heat Poor Air Quality | Reduces heat island effect, mitigates through carbon sequestration | Parks, Recreation, and Waterfront Department - Parks Division - Urban Forestry Unit | Parks Tax State of CA Environmental Enhancement and Mitigation Project Grant State of CA Urban Greening Grant Urban and Commuity Forestry Grants through the Inflation Reduction Act | Short term (grant-funded efforts will be completed by end of FY27) and ongoing
Reduce Berkeley’s vulnerability to severe storms and associated hazards through proactive research and planning, zoning regulations, and improvements to stormwater drainage facilities. | Use development standards to ensure that new development does not contribute to an increase in flood potential. | Medium | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Planning Department: Land Use Division | City General Fund | Ongoing
Reduce Berkeley’s vulnerability to severe storms and associated hazards through proactive research and planning, zoning regulations, and improvements to stormwater drainage facilities. | Design public improvements such as streets, parks and plazas, for retention and infiltration of stormwater by diverting urban runoff to bio- filtration systems. | Medium | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Public Works: Engineering | City General Fund Permit Service Center Enterprise Fund Measure M Bond Funds Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) | Ongoing
Reduce Berkeley’s vulnerability to severe storms and associated hazards through proactive research and planning, zoning regulations, and improvements to stormwater drainage facilities. | Renovate all eight tide tubes that remove storm water from Berkeley Aquatic Park and Potter Street to the Bay. | Medium | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Parks, Recreation, and Waterfront Department | Promoting Resilient Operations for Transformative, Efficient, and Cost-saving Transportation Program (PROTECT) Grant Parks Tax | Medium Term (3-5 years)
Reduce Berkeley’s vulnerability to severe storms and associated hazards through proactive research and planning, zoning regulations, and improvements to stormwater drainage facilities. | Complete a Stormwater Master Plan for all City stormwater infrastructure, to identify system deficiencies, establish a capital stormwater improvement plan, and identify funding mechanisms. | Medium | Flood | Flooding disproprtonally impacts in South and West Berkeley. | Public Works: Engineering | City Stormwater Fund ($1.5M) City General Fund ($400k) | Short term (1-5 years)
Reduce fire risk in existing development through fire code updates and enforcement. | Continue to evaluate inspection procedures and adjust inspection cycle annually based on changing climatic conditions. | High | WUI Fire | Wilfires disproportionately impact people with access and functional needs and ensuring inspections are up to date reduces risk. | Fire Department - WUI Division | Measure FF | Ongoing
Reduce fire risk in existing development through fire code updates and enforcement. | Maintain Fire Department efforts to reduce fire risk through inspections through annual building inspections in all Fire Zones, including Multi-unit-residential building inspections. | High | WUI Fire | Multi-unit housing is more affordable and serves a large percentage of socially vulnerable and underserved communities. Inspections help to ensure the safety of this housing stock. | Fire Department: Fire Prevention Division | City General Fund UC Settlement Fund | Ongoing
Reduce fire risk in existing development through fire code updates and enforcement. | Maintain Fire Department efforts to reduce fire risk through Defensible Space Inspections in Fire Zones 2 and 3. | High | WUI Fire | Provides career and workforce development in public safety for local youth. | Fire Department: WUI Division | Measure FF YouthWorks Program funds | Ongoing
Reduce fire risk in existing development through fire code updates and enforcement. | Continue YouthWorks pilot program to staff expansion of Defensible Space inspections in Fire Zones 2 and 3. | High | WUI Fire | Provides career and workforce development in public safety for local youth. | Fire Department - WUI Division | Measure FF Youth Works Program funds | Ongoing
Reduce fire risk in existing development through fire code updates and enforcement. | Continue to periodically update the Berkeley Fire Code and adopt the California Fire Code with local amendments to incorporate the latest knowledge and State regulations to protect people and property against known risks in both structural and non-structural building and site components. | High | WUI Fire | The Fire Code inorporates the latest knowledge in protecting the diverse buildings that house the Berkleey community. | Fire Department: Fire Prevention Division | City General Fund UC Settlement Fund Permit Service Center Enterprise Fund | Ongoing
Reduce fire risk in existing development through vegetation management. | Explore additional options to provide collaborative, citywide vegetation management on private and public property. | High | WUI Fire | Expand access to vegetation management. | Fire Department - WUI Division | Measure FF | Short term (1-5 years)
Reduce fire risk in existing development through vegetation management. | Maintain Weekly Curbside Plant Debris Collection | High | WUI Fire | Expand access to vegetation management. | Public Works Department: Zero Waste Division | City General Fund Refuse Fee | Ongoing
Reduce fire risk in existing development through vegetation management. | Pursue external funding to perform vegetation management on public and private property and to increase education and awareness of vegetation management standards for fire fuel reduction, home hardening, and ignition controls. | High | WUI Fire | Expand access to vegetation management. | Fire Department - WUI Division | Measure FF City General Fund | Ongoing
Reduce fire risk in existing development through vegetation management. | Maintain Fire Fuel Debris Bin Program | High | WUI Fire | Expand access to vegetation management. | Public Works Department: Zero Waste Division | City General Fund Refuse Fee | Ongoing
Reduce fire risk in existing development through vegetation management. | Maintain Fire Fuel Abatement Program on Public Land with technical assistance from WUI Division | High | WUI Fire | Expand access to vegetation management. | PRW: Senior Landscape Supervisor WUI Division | City General Fund Refuse Fee Measure FF | Ongoing
Reduce fire risk in existing development through vegetation management. | Continue to allocate UC Settlement Funding to do vegetation management projects on UC Berkeley properties. | High | WUI Fire | Expand access to vegetation management. | Fire Department - WUI Division | UC Settlement Fund | Ongoing
Reduce fire risk in existing development through vegetation management. | Maintain redesigned and expanded citywide fire fuel chipper program to provide curbside pickup, chipping, and disposal of vegetation material from residential properties. | High | WUI Fire | Expanded program provides access to vegetation management support to all City residents and is no longer limited. | Fire Department - WUI Division | Measure FF | Ongoing
Reduce fire risk through residential assistance program. | Continue to implement Resident Assistant Program pilot to provide home hardening materials and defensible space materials and instructions to low income residents in targeted high fire risk areas. | High | WUI Fire | Provides subsidized materials to residents at greatest risk of WUI fire. | Fire Department - WUI Division | Measure FF | Short term (1-5 years)
Reduce fire risk through utility undergrounding. | Urge PG&E to perform utility undergrounding in Berkeley's Very High Fire Hazard Severity Zone (VHFHSZ) to mitigate wildfire risk and limit evacuation and ingress obstruction. Coordinate efforts with the State of CA Public Utilities Commsission, and elected officials. | High | WUI Fire Earthquake High Wind | Berkeley's Very High Fire Severity Zone has residents with access and functional needs that may have trouble evucuating in a wildfire. | Berkeley City Council | City General Fund | Short term (1-5 years)
Reduce hazard vulnerabilities for non-City-owned buildings throughout Berkeley. | Continue to periodically update and adopt the California Building Standards Code with local amendments to incorporate the latest knowledge and design standards to protect people and property against known seismic, fire, flood and landslide risks in both structural and non-structural building and site components. | High | Multihazard | Underserved communities live in old housing stock and multi-family buildings. | Planning Department: Building and Safety Division | City General Fund | Ongoing
Reduce hazard vulnerabilities for non-City-owned buildings throughout Berkeley. | Explain requirements and provide guidance to owners of potentially hazardous structures to facilitate retrofit, including owners participating in the Earthquake Brace and Bolt program, Earthquake Soft Story Program, and those applying for Transfer Tax rebates. | High | Multihazard | Underserved communities live in old housing stock and multi-family buildings. | Planning Department: Building and Safety Division Finance Department (for Transfer Tax applications and disbursement) | City General Fund | Ongoing
Reduce wildfire risk throughout Berkeley by implementing the Action Plan identified in the Community Wildfire Protection Plan (CWPP). | Implement the Action Plan in the CWPP. | High | WUI Fire | The CWPP has identified actions that support low income residents in conducting home hardening and vegetation management. | Fire Department: WUI Division | Measure FF Cal Fire Grants | Ongoing
Research, identify, and implement infrastructure improvements to facilitate emergency evacuation. | Complete implementation of the Evacuation and Response Time Study to identify necessary roadway safety improvements, along with prioritized roadways, to facilitate safe evacuation during emergency scenarios. | High | Multihazard | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Fire Department | Measure FF | Short term (1-5 years)
Research, identify, and implement infrastructure improvements to facilitate emergency evacuation. | Complete evacuation analysis required by new State evacuation laws under SB99, AB747, and AB1409. Incorporate findings into the updated Safety Element of the General Plan. | High | Multihazard | Evacuation is more difficult for people with disabilities and people with access and functional needs. | Fire Department: Office of Emergency Services | Measure FF | Short term (1-5 years)
Streamline the zoning permitting process to rebuild residential and commerical structures following disasters. | Give priority to project applications that would rebuild to current standards following disasters. | Low | Multihazard | This makes it easier to rebuild post diaster, hopefully allowing for diverse populations to stay in Berkeley. | Planning Department: Land Use Division | City General Fund | Short term (1-5 years)
Strengthen or replace City buildings in the identified prioritized order as funding is available. | West Berkeley Service Center Old City Hall Veterans Memorial Building | High | Multihazard | City facilities and structures serve socially vulnerable populations day to day and during emergencies. | Public Works Department: Supervising Civil Engineer for Facilities | Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) City General Fund T1 Bond | Ongoing
Strengthen or replace City buildings in the identified prioritized order as funding is available. | Continue to seek funding to seismically strengthen or replace additional City buildings in a prioritized order. | High | Multihazard | City facilities and structures serve socially vulnerable populations day to day and during emergencies. | Public Works Department: Supervising Civil Engineer for Facilities | Building Resilient Infrastructure and Communities (BRIC) Grant Program Hazard Mitigation Grant Program (HMGP) City General Fund T1 Bond | Ongoing
Strengthen or replace City buildings in the identified prioritized order as funding is available. | MLK Junior Youth Services Center, Williard Clubhouse, African American Holistic Resource Center. | High | Multihazard | The Center operates a lot of free programs for the Berkeley community. | Parks, Recreation, and Waterfront Department | City General Fund T1 Bond Parks Tax | Short term (1-5 years)

## Other Actions Considered
Action Description | Proposed Activities | Priority Level | Related Natural Hazard(s) | How would this benefit underserved communities and socially vulnerable populations? | Lead Office, Division, or Department | Funding Sources | Timeline | Notes
Reduce fire risk in existing development through vegetation management. | Explore options for developing a City-run hand crew to implement vegetation management projects on public and private property. | High | WUI Fire | Expand access to vegetation management. Potential workforce development opportunity people who were formerly incarcerated. | Fire Department - WUI Division | Measure FF | Long Term | Action considered but for longer time than in the next five years.
Reduce fire risk through community-focused education, training, and fire code updates. | Conduct multi-unit-residential building inspections in all Fire Zones. | High | WUI Fire | Lower income people live in multi-residential-unit housing. | Fire Department - Fire Prevention | General Fund | Ongoing | Goal, but need more capacity
Reduce fire risk through community-focused education, training, and fire code updates. | Using community volunteers, thorugh WUI Ambassador Program, to educate people city-wide on vegetation management, home hardening, and defensible space. | High | WUI Fire | Expand access to educational programs and reach people who would not otherwise receive information. | Fire Department - WUI Division | Measure FF | Short term (1-5 years) | Pilot program in 2023-24, need to evaluate what next steps might be
Reduce fire risk through community-focused education, training, and fire code updates. | Conduct annual building inspections in all Fire Zones. | High | WUI Fire |  | Fire Department - Fire Prevention | General Fund | Ongoing | Goal, but need more capacity
Advance opportunities for water reuse. | Research and support opportunities to advance purple pipe implementation. | Medium | Multi | Increases the security of Berkeley's water supplies from climate change impacts for all residents | Planning and Public Works | EBMUD is expected to fund | 2024-2030 (estimated) | Goal, but not the top of the priority list
Reduce Berkeley’s vulnerability to extreme heat events and associated hazards. | Tree planting/urban forestry program | High | Poor Air Quality, Extreme Heat | Reduces heat island effect, mitigates through carbon sequestration | Parks and Rec | In progress; needs PRW vetting and input | In progress; needs PRW vetting and input | Some new actions included around urban forestry, but room to build out more capacity in the future
Reduce flood risk | Nature based solutions at shoreline | Medium | Flooding | Underserved communities are most likely to live in/near areas that would be impacted | Public Works and Parks | Needs PRW/PW vetting and input | Needs PRW/PW vetting and input | Some new actions included around nature based solutions on the shoreline, but room to build out more capacity in the future
Implement existing City programs, plans, and projects designed to reduce emissions that contribute to poor air quality. | Continue to manage on-street parking and maintain City parking garages to reduce emissions by making it easier to find a parking space more quickly (reducing the time spent circling around looking for parking). | Air Quality | Extreme Heat, Poor Air Quality | Poor air quality disproportionately impacts communities of color, and South and West Berkeley. | Public Works Department - Transportation Division | City funds, County Transportation Sales Tax, and Grant Funding | Ongoing | This is something that the City does and has infrastructure for, but not entirely sure the research is there that it helps reduce emissions. Further work to expand air quality mitigation measures for next round
Strengthen or replace City buildings in the identified prioritized order as funding is available. | South Berkeley Senior Center | High | Multihazard | The South Berkeley Senior Center serves South Berkeley, the area of Berkeley with higher numbers of people of color and low income residents. | Parks, Recreation, and Waterfront Department | CRC grant | Short term (1-5 years) | The City applied for a CRC grant to fund this effort, but was not awarded. New funding must be identified.